## Original
Job Cost Budget
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Contract Amount: | 167020 |  | Thru CO # | 0 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 2000 |  | -2000 |  |  | 26.6667
|  | Clean-up | 2500 |  | -2500 |  |  | 33.3333
|  | Delivery | 1000 |  | -1000 |  |  | 13.3333
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 1170 |  | -1170 |  |  | 15.6
|  | Rough Carpentry | 3451 |  | -3451 |  |  | 46.0133
|  | Finish Carpentry | 12075 |  | -12075 |  |  | 161
|  | Doors | 4200 |  | -4200 |  |  | 56
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 7493 |  | -7493 |  |  | 99.9067
|  | Insulation | 974 |  | -974 |  |  | 12.9867
|  | Drywall | 18210 |  | -18210 |  |  | 242.8
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 2450 |  | -2450 |  |  | 32.6667
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 55523 | 0 | -55523 |  |  | 740.3067 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 21290 |  | -21290
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 21290 | 0 | -21290
3 | Subcontractors
|  | Acoustical Ceilings | 53969 |  | -53969
|  | Taping | 12780 |  | -12780
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 66749 | 0 | -12780
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency (from ceiling options) | 0 |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Contract Amount | Estimated Profit | Percent
| Overall Job Totals |  | 143562 | 167020 | 23458 | 0.14045

## CO1
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 15430 |  | CO # | 1 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 660 |  | -660 |  |  | 8.8
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 660 | 0 | -660 |  |  | 8.8 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
|  | Acoustical Ceilings | 9250
|  | Taping | 1721 |  | -1721
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 10971 | 0 | -1721
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference | Percent
| Overall Job Totals |  | 11631 | 15430 | 3799 | 24.62%

## CO2
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 161
| Change Amount: | 930 |  | CO # | 2 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 0 | 930 | 930 | 100%

## CO3
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 360 |  | CO # | 3 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 313 |  | -313 |  |  | 4.1733
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 313 | 0 | -313 |  |  | 4.1733 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 313 | 360 | 47 | 13.06%

## Updated Budget
Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Updated Contract : | 183740 |  | CO # | 3 |  |  | 2025-06-04
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 2000 |  | -2000 |  |  | 26.6667 | 91
|  | Clean-up | 2500 |  | -2500 |  |  | 33.3333 | 125
|  | Delivery | 1000 |  | -1000 |  |  | 13.3333 | 13
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0 | 16
|  | Layout | 1170 |  | -1170 |  |  | 15.6
|  | Rough Carpentry | 3451 |  | -3451 |  |  | 46.0133 | 48
|  | Finish Carpentry | 12388 |  | -12388 |  |  | 165.1733 | 309
|  | Doors | 4200 |  | -4200 |  |  | 56 | 34.5
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 7493 |  | -7493 |  |  | 99.9067 | 38
|  | Insulation | 974 |  | -974 |  |  | 12.9867 | 104
|  | Drywall | 18210 |  | -18210 |  |  | 242.8
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 3110 |  | -3110 |  |  | 41.4667
|  | Untion Dues | 0 | 9320.83 | 9320.83 |  |  | 0
|  | Overtime | 0 | 28605.71 | 28605.71 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0 | 4
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 56496 | 37926.54 | -18569.46 | 67.13% |  | 753.28 | 782.5 | -29.22
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 21290 |  | -21290
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  | 12623.32 | 12623.32
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 21290 | 12623.32 | -8666.68 | 59.29%
3 | Subcontractors
|  | Acoustical Ceilings | 63219
|  | Taping | 14501 | 70696.1 | 56195.1
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 77720 | 70696.1 | 56195.1 | 90.96%
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Contract Amount | Estimated Profit | Percent | Total Actual
| Overall Job Totals |  | 155506 | 183740 | 28234 | 15.37% | 121245.96 | 77.97%