## Original
Job Cost Budget
| Project Name: | LVV-HP 3&5 |  | Job # | 186
| Contract Amount: | 740000 |  | Thru CO # | 0 |  |  | Last Update | 2026-03-02
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 8000 |  | -8000 |  |  | 106.6667 | 104.5 | 2.1667
|  | Clean-up | 7000 |  | -7000 |  |  | 93.3333 | 266 | -172.6667
|  | Delivery | 2831 |  | -2831 |  |  | 37.7467 | 20.5 | 17.2467
|  | Temp Protections | 0 |  | 0 |  |  | 0 | 11 | -11
|  | Demo | 1950 |  | -1950 |  |  | 26 | 34.5 | -8.5
|  | Layout | 2000 |  | -2000 |  |  | 26.6667 | 46 | -19.3333
|  | Rough Carpentry | 6533 |  | -6533 |  |  | 87.1067 | 81 | 6.1067
|  | Finish Carpentry (Cabinets) | 6825 |  | -6825 |  |  | 91 | 508 | -417
|  | Doors With Trim | 5000 |  | -5000 |  |  | 66.6667 | 85 | -18.3333
|  | Exterior Framing | 0 |  | 0 |  |  | 0 |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0 |  | 0
|  | Interior Framing | 26278 |  | -26278 |  |  | 350.3733 | 259.5 | 90.8733
|  | Insulation | 8182 |  | -8182 |  |  | 109.0933 | 61.5 | 47.5933
|  | Drywall | 20358 |  | -20358 |  |  | 271.44 | 318 | -46.56
|  | Taping | 0 |  | 0 |  |  | 0 |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0 |  | 0
|  | Grid | 0 |  | 0 |  |  | 0 | 61 | -61
|  | Specialties | 1800 |  | -1800 |  |  | 24 | 51 | -27
|  | Flooring | 0 |  | 0 |  |  | 0 |  | 0
|  | Caulking | 2980 |  | -2980 |  |  | 39.7333 | 60 | -20.2667
|  | Wire Shelving | 2610 |  | -2610 |  |  | 34.8 |  | 34.8
|  | Onyx Tops and Showers | 3600 |  | -3600 |  |  | 48 |  | 48
|  | Other | 0 |  | 0 |  |  | 0 | 16.5 | -16.5
|  | Trim | 13039 |  | -13039 |  |  | 173.8533 |  | 173.8533
|  | WO# | 0 |  | 0 |  |  | 0 | 12 | -12
|  | Painting | 0 |  | 0 |  |  | 0 | 2 | -2
|  | Labor Sub Totals | 118986 | 139613.91 | -118986 |  |  | 1586.48 | 1998 | -411.52
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 110216 |  | -110216
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 110216 | 0 | -110216
3 | Subcontractors
|  | Final Clean | 3500 |  | -3500
|  | CKF Tops | 20660 |  | -20660
|  | Shower Doors | 9000
|  | Taping C4 | 21500
|  | Great Plains Tile | 4350
|  | FDC Flooring | 22112
|  | Switzer Painting | 28000
|  | Blinds | 13000 |  | -13000
|  | Jayhawk Sprinkler | 28670
|  | Echo GPS | 1500
|  | JF Denney Plumbing | 65218
|  | McGlinn Heating and Cooling | 9000
|  | Keller Fire | 24786
|  | Tech Electric | 115000 |  | -115000
|  | Subcontractor Totals | 366296 | 0 | -148660
4 | Other
|  | Equipment Rental | 4125 |  | -4125
|  | Permit | 3750 |  | -3750
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding | 0 |  | 0
|  | Allowance | 12000 |  | -12000
|  | Contingency | 20000 |  | -20000
0
|  | Other Sub Totals | 39875 | 0 | -39875
|  |  | Budget | Contract Amount | Estimated Profit | Percent
| Overall Job Totals |  | 635373 | 740000 | 104627 | 14.14%

## CO1
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 15430 |  | CO # | 1 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 660 |  | -660 |  |  | 8.8
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 660 | 0 | -660 |  |  | 8.8 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
|  | Acoustical Ceilings | 9250
|  | Taping | 1721 |  | -1721
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 10971 | 0 | -1721
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference | Percent
| Overall Job Totals |  | 11631 | 15430 | 3799 | 24.62%

## CO2
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 161
| Change Amount: | 930 |  | CO # | 2 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 0 | 930 | 930 | 100%

## CO3
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 360 |  | CO # | 3 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 313 |  | -313 |  |  | 4.1733
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 313 | 0 | -313 |  |  | 4.1733 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 313 | 360 | 47 | 13.06%

## Updated Budget
Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Updated Contract : | 183740 |  | CO # | 3 |  |  | 2025-06-04
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 2000 |  | -2000 |  |  | 26.6667 | 91
|  | Clean-up | 2500 |  | -2500 |  |  | 33.3333 | 125
|  | Delivery | 1000 |  | -1000 |  |  | 13.3333 | 13
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0 | 16
|  | Layout | 1170 |  | -1170 |  |  | 15.6
|  | Rough Carpentry | 3451 |  | -3451 |  |  | 46.0133 | 48
|  | Finish Carpentry | 12388 |  | -12388 |  |  | 165.1733 | 309
|  | Doors | 4200 |  | -4200 |  |  | 56 | 34.5
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 7493 |  | -7493 |  |  | 99.9067 | 38
|  | Insulation | 974 |  | -974 |  |  | 12.9867 | 104
|  | Drywall | 18210 |  | -18210 |  |  | 242.8
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 3110 |  | -3110 |  |  | 41.4667
|  | Untion Dues | 0 | 9320.83 | 9320.83 |  |  | 0
|  | Overtime | 0 | 28605.71 | 28605.71 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0 | 4
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 56496 | 37926.54 | -18569.46 | 67.13% |  | 753.28 | 782.5 | -29.22
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 21290 |  | -21290
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  | 12623.32 | 12623.32
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 21290 | 12623.32 | -8666.68 | 59.29%
3 | Subcontractors
|  | Acoustical Ceilings | 63219
|  | Taping | 14501 | 70696.1 | 56195.1
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 77720 | 70696.1 | 56195.1 | 90.96%
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Contract Amount | Estimated Profit | Percent | Total Actual
| Overall Job Totals |  | 155506 | 183740 | 28234 | 15.37% | 121245.96 | 77.97%