## Original
Job Cost Budget
| Project Name: | ISD Fairmount 2026 |  | Job # | 222
| Contract Amount: | 2010000 |  | Thru CO # | 0 |  |  | Last Update | 2026-05-19
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 27750 |  | -27750 |  |  | 370
|  | Clean-up | 27750 |  | -27750 |  |  | 370
|  | Delivery | 3500 |  | -3500 |  |  | 46.6667
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 4120 |  | -4120 |  |  | 54.9333
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 34062 |  | -34062 |  |  | 454.16
|  | Sheathing | 5842 |  | -5842 |  |  | 77.8933
|  | Interior Framing | 131331 |  | -131331 |  |  | 1751.08
|  | Insulation | 25168 |  | -25168 |  |  | 335.5733
|  | Drywall | 202637 |  | -202637 |  |  | 2701.8267
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 624 |  | -624 |  |  | 8.32
|  | Caulking | 20192 |  | -20192 |  |  | 269.2267
|  | Overtime Hrs | 0 |  | 0 |  |  | 0
|  | Patching | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 482976 | 0 | -482976 |  |  | 6439.68 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 275939 |  | -275939
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 275939 | 0 | -275939
3 | Subcontractors
|  | K Buildings | 80690 |  | -80690
|  | Taping C4 | 147390 |  | -147390
|  | Briarwood | 755569 |  | -755569
0
|  | Subcontractor Totals | 983649 | 0 | -902959
4 | Other
|  | Equipment Rental | 15620 |  | -15620
|  | Engineering | 2900 |  | -2900
|  | Allowance |  |  | 0
|  | Contingency | 20000 |  | -20000
0
|  | Other Sub Totals | 38520 |  | -38520
|  |  | Budget | Contract Amount | Estimated Profit | Percent
| Overall Job Totals |  | 1781084 | 2010000 | 228916 | 11.39%

## SOV
Brighten SOV
ISD Fairmount 2026
Pre-Con | 20000
Material | 295000
Exterior Framing and Sheathing Labor | 85000
Interior Framing Labor | 200000
Drywall Labor | 300000
Insulation Labor | 50000
Equipment | 30000
Taping/Finishing Subcontractor | 150000
Insualtion Subcontractor | 85000
Acoustical Subcontractor | 795000
Contract Amount | 2010000

## CO1
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 15430 |  | CO # | 1 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 660 |  | -660 |  |  | 8.8
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 660 | 0 | -660 |  |  | 8.8 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
|  | Acoustical Ceilings | 9250
|  | Taping | 1721 |  | -1721
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 10971 | 0 | -1721
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference | Percent
| Overall Job Totals |  | 11631 | 15430 | 3799 | 24.62%

## CO2
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 161
| Change Amount: | 930 |  | CO # | 2 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 0 | 930 | 930 | 100%

## CO3
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 360 |  | CO # | 3 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 313 |  | -313 |  |  | 4.1733
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 313 | 0 | -313 |  |  | 4.1733 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 313 | 360 | 47 | 13.06%

## Updated Budget
Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Updated Contract : | 183740 |  | CO # | 3 |  |  | 2025-06-04
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 2000 |  | -2000 |  |  | 26.6667 | 91
|  | Clean-up | 2500 |  | -2500 |  |  | 33.3333 | 125
|  | Delivery | 1000 |  | -1000 |  |  | 13.3333 | 13
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0 | 16
|  | Layout | 1170 |  | -1170 |  |  | 15.6
|  | Rough Carpentry | 3451 |  | -3451 |  |  | 46.0133 | 48
|  | Finish Carpentry | 12388 |  | -12388 |  |  | 165.1733 | 309
|  | Doors | 4200 |  | -4200 |  |  | 56 | 34.5
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 7493 |  | -7493 |  |  | 99.9067 | 38
|  | Insulation | 974 |  | -974 |  |  | 12.9867 | 104
|  | Drywall | 18210 |  | -18210 |  |  | 242.8
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 3110 |  | -3110 |  |  | 41.4667
|  | Untion Dues | 0 | 9320.83 | 9320.83 |  |  | 0
|  | Overtime | 0 | 28605.71 | 28605.71 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0 | 4
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 56496 | 37926.54 | -18569.46 | 67.13% |  | 753.28 | 782.5 | -29.22
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 21290 |  | -21290
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  | 12623.32 | 12623.32
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 21290 | 12623.32 | -8666.68 | 59.29%
3 | Subcontractors
|  | Acoustical Ceilings | 63219
|  | Taping | 14501 | 70696.1 | 56195.1
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 77720 | 70696.1 | 56195.1 | 90.96%
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Contract Amount | Estimated Profit | Percent | Total Actual
| Overall Job Totals |  | 155506 | 183740 | 28234 | 15.37% | 121245.96 | 77.97%