## Original
Job Cost Budget
| Project Name: | LPS Heritage Middle |  | Job # | 163
| Contract Amount: | 981200 |  | Thru CO # | 0 |  |  | Last Update | 2025-09-27
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 11500 |  | -11500 |  |  | 153.3333 | 253.67
|  | Clean-up | 10485 |  | -10485 |  |  | 139.8 | 195.5
|  | Delivery | 3400 |  | -3400 |  |  | 45.3333 | 60
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 3800 |  | -3800 |  |  | 50.6667 | 74.5
|  | Rough Carpentry | 11100 |  | -11100 |  |  | 148
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0 | 294
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 94495 |  | -94495 |  |  | 1259.9333 | 592.67
|  | Insulation | 9195 |  | -9195 |  |  | 122.6 | 16
|  | Drywall | 109714 |  | -109714 |  |  | 1462.8533 | 1387.42
|  | Taping | 0 |  | 0 |  |  | 0
|  | Caulking | 0 |  | 0 |  |  | 0 | 51
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0 | 97
|  | Other | 0 |  | 0 |  |  | 0 | 14
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0 | 62.5
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 253689 | 0 | -253689 |  |  | 3382.52 | 3098.26
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 149356 |  | -149356
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 149356 | 0 | -149356
3 | Subcontractors
|  | Acoustical Ceilings (Briarwood) | 245769 |  | -245769
|  | Taping (C4) | 92850 |  | -92850
|  | Spray Foam (KC Plaster) | 19000 |  | -19000
|  | Other |  |  | 0
|  | Subcontractor Totals | 357619 | 0 | -111850
4 | Other
|  | Equipment Rental | 17600 |  | -17600
|  | Engineering | 2500 |  | -2500
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding | 25130 |  | -25130
|  | Allowance | 15000 |  | -15000
|  | Contingency | 20000 |  | -20000
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 80230 | 0 | -80230
|  |  | Budget | Contract Amount | Estimated Profit | Percent
| Overall Job Totals |  | 840894 | 981200 | 140306 | 14.3%

## Updated Budget
Budget Update
| Project Name: | LPS Heritage Middle |  | Job # | 163 |  | 2026-02-13
| Updated Contract : | 990056.88 | [5 empty] | 2026-05-21
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 11500 |  | -11500 |  |  | 153.3333
|  | Clean-up | 10485 |  | -10485 |  |  | 139.8
|  | Delivery | 3400 |  | -3400 |  |  | 45.3333
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 3800 |  | -3800 |  |  | 50.6667
|  | Rough Carpentry | 11100 |  | -11100 |  |  | 148
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 94495 |  | -94495 |  |  | 1259.9333
|  | Insulation | 9195 |  | -9195 |  |  | 122.6
|  | Drywall | 109714 |  | -109714 |  |  | 1462.8533
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Change Order 3 - RFI 36 | 560
|  | Change Order 1 - Secure Entry Walls and Openings | 4060 |  |  |  |  | 54.1333 | 4
|  | Change Order 2 - CE #004 - PR001 | -12117.8 |  |  |  |  | -161.5707
|  | Change Order 4 - Exterior Wall furrring | 8400
|  | Change Order 5 - PR06 | 3150
|  | Change Order 6 - CCD003 | 350
|  | Change Order 7 - Plaster Patching at Stairwell Ceilings | 0
|  | Change Order 8 - C4 OT | 0
|  | Change Order 9 - Extra 1 st flr framing | 900
|  | Allowance | 6820
|  | Labor Sub Totals | 265811.2 | 228880 | -253689 | 86.11% |  | 3275.0827 | 4 | 3271.0827
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 149356 |  | -149356
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Change Order 3 - RFI 36 | 777.79 | 777.79 | 0
|  | Change Order 1 - Secure Entry Walls and Openings | 1253.9 | 1253.9 | 0
|  | Change Order 2 - CE #004 - PR001 | -29640.62 | -29640.62 | 0
|  | Change Order 4 - Exterior Wall furrring | 3957.88 | 3957.88
|  | Change Order 5 - PR06 | 1465.62 | 1465.62
|  | Change Order 6 - CCD003 | 279.57 | 279.57
|  | Change Order 7-9 | 1000
|  | Allowance Materials | 1982
|  | Material Sub Totals | 130432.14 | -21905.86 | -149356
|  | Material Sub Totals | 130432.14 | -27608.93 | -149356 | -21.17%
3 | Subcontractors
|  | Acoustical Ceilings (Briarwood) | 245769 |  | -245769
|  | Taping (C4) | 92850 |  | -92850
|  | Spray Foam (KC Plaster) | 19000 |  | -19000
|  | Other |  |  | 0
|  | Subcontractor Totals | 357619 | 0 | -111850 | 0%
4 | Other
|  | Equipment Rental | 17600 |  | -17600
|  | Engineering | 2500 |  | -2500
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding | 25130 |  | -25130
|  | Allowance |  |  | 0
|  | Contingency | 20000 |  | -20000
|  | Dumpster |  |  | 0
|  | Change Order Equipment Rental 2 | -1046.13
|  | Other Sub Totals | 64183.87 | 0 | -2500
|  |  | Budget | Contract Amount | Estimated Profit | Percent | Total Actual
| Overall Job Totals |  | 818046.21 | 979267.6 | 161221.39 | 16.46% |  | 0%

## CO1
CO Budget Update
| Project Name: | LPS Heritage Middle |  | Job # | 163
| Change Amount: | -6720.01 |  | Thro CO # | 3 |  |  | Last Update | 2026-05-21
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Change Order 3 - RFI 36 | 560 | 560 | 0
|  | Change Order 1 - Secure Entry Walls and Openings | 4060 | 4060 | 0
|  | Change Order 2 - CE #004 - PR001 | -12117.8 | -12117.8 | 0
|  | Labor Sub Totals | -7497.8 | -7497.8 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Change Order 3 - RFI 36 | 777.79 | 777.79
|  | Change Order 1 - Secure Entry Walls and Openings | 1253.9 | 1253.9
|  | Change Order 2 - CE #004 - PR001 | -29640.62 | -29640.62
|  | Material Sub Totals | 777.79 | 777.79 | 0
3 | Subcontractors
|  | Acoustical Ceilings | 0
|  | Taping | 0 |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference | Percent
| Overall Job Totals |  | -6720.01 | -6720.01 | 0 | 0%

## CO2
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 161
| Change Amount: | 930 |  | CO # | 2 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 0 | 930 | 930 | 100%

## CO3
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 360 |  | CO # | 3 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 313 |  | -313 |  |  | 4.1733
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 313 | 0 | -313 |  |  | 4.1733 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 313 | 360 | 47 | 13.06%