## Original
Job Cost Budget
| Project Name: | LightEgde Data Center |  | Job # | 204
| Contract Amount: | 335450 |  | Thru CO # | 0 |  |  | Last Update | 2026-01-08
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 7500 |  | -7500 |  |  | 100
|  | Clean-up | 9000 |  | -9000 |  |  | 120
|  | Delivery | 2500 |  | -2500 |  |  | 33.3333
|  | Temp Protections | 1200 |  | -1200 |  |  | 16
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 2831 |  | -2831 |  |  | 37.7467
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 12600 |  | -12600 |  |  | 168
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 53805 |  | -53805 |  |  | 717.4
|  | Insulation | 5477 |  | -5477 |  |  | 73.0267
|  | Drywall | 36290 |  | -36290 |  |  | 483.8667
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 900 |  | -900 |  |  | 12
|  | Ceiling Tile | 600 |  | -600 |  |  | 8
|  | Wire Mesh | 12955 |  | -12955 |  |  | 172.7333
|  | Caulking | 11783 |  | -11783 |  |  | 157.1067
|  | Vapor Barrier | 4810 |  | -4810 |  |  | 64.1333
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 162251 | 0 | -162251 |  |  | 2163.3467 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 75015 |  | -75015
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 75015 | 0 | -75015
3 | Subcontractors
|  | Acoustical Ceilings - Briarwood | 0 |  | 0
|  | Taping - C4 | 31700 |  | -31700
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 31700 | 0 | -31700
4 | Other
|  | Equipment Rental | 5005 |  | -5005
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 5005 | 0 | 0
|  |  | Budget | Actual | Difference
| Overall Job Totals |  | 273971 |  |  |  | 61479 | 18.33%

## SOV
Jan
Pre-Con | 4000 | 0.5 | 2000
D&E Framing | 19000
D&E Drywall | 38500
D&E DFHW | 2615
D&E ACT | 3200
DH4 Framing | 57600
DH4 Security Mesh and Poly Vapor Barrier | 29950
DH4 Drywall | 158265
DH4 DFHW | 14515
Equipment | 5005
Temp Dust Partition | 2800 | 1 | 2800
Contract amount | 335450

## CO1
CO Budget Update
| Project Name: |  |  | Job #
| Change Amount: |  |  | CO # | 0 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference
| Overall Job Totals |  | 0

## CO2
CO Budget Update
| Project Name: |  |  | Job #
| Change Amount: |  |  | CO # | 0 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference
| Overall Job Totals |  | 0

## CO3
CO Budget Update
| Project Name: |  |  | Job #
| Change Amount: |  |  | CO # | 0 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference
| Overall Job Totals |  | 0

## Updated Budget
CO Budget Update
| Project Name: |  |  | Job #
| Change Amount: |  |  | CO # | 0 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference
| Overall Job Totals |  | 0