## Original
Job Cost Budget
| Project Name: | LVV-HP A211, 311, & 317 |  | Job # | 206
| Contract Amount: | 665000 |  | Thru CO # | 0 |  |  | Last Update | 2026-02-24
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 9000 |  | -9000 |  |  | 120
|  | Clean-up | 9000 |  | -9000 |  |  | 120
|  | Delivery | 1000 |  | -1000 |  |  | 13.3333
|  | Temp Protections | 1500 |  | -1500 |  |  | 20
|  | Demo | 1493 |  | -1493 |  |  | 19.9067
|  | Layout | 1500 |  | -1500 |  |  | 20
|  | Rough Carpentry | 5856 |  | -5856 |  |  | 78.08
|  | Finish Carpentry (Cabinets) | 6225 |  | -6225 |  |  | 83
|  | Doors With Trim | 6600 |  | -6600 |  |  | 88
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 25412 |  | -25412 |  |  | 338.8267
|  | Insulation | 11068 |  | -11068 |  |  | 147.5733
|  | Drywall | 19547 |  | -19547 |  |  | 260.6267
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 2150 |  | -2150 |  |  | 28.6667
|  | Flooring | 0 |  | 0 |  |  | 0
|  | Caulking | 2946 |  | -2946 |  |  | 39.28
|  | Wire Shelving | 2374
|  | Onyx Tops and Showers | 3500
|  | Allowance Hrs | 0 |  | 0
|  | Trim | 8978
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 118149 | 0 | -103297 |  |  | 1377.2933 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 99630 |  | -99630
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 99630 | 0 | -99630
3 | Subcontractors
|  | Final Clean | 3500 |  | -3500
|  | CKF Tops | 15342.73 |  | -15342.73
|  | Shower Doors | 5000
|  | Taping C4 | 14999
|  | Great Plains Tile | 5800
|  | FDC Flooring | 22914
|  | Switzer Painting | 27980
|  | Blinds | 8117.06 |  | -8117.06
|  | Jayhawk Sprinkler | 26175
|  | Echo GPS | 1500
|  | JF Denney Plumbing | 65430
|  | McGlinn Heating and Cooling | 8500
|  | Keller Fire | 15950.3
|  | Tech Electric | 112000 |  | -112000
|  | Subcontractor Totals | 333208.09 | 0 | -135459.79
4 | Other
|  | Equipment Rental | 3025 |  | -3025
|  | Permit | 3200 |  | -3200
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding | 0 |  | 0
|  | Allowance | 15000 |  | -15000
|  | Contingency | 5000 |  | -5000
0
|  | Other Sub Totals | 26225 | 0 | -26225
|  |  | Budget | Contract Amount | Estimated Profit | Percent
| Overall Job Totals |  | 577212.09 | 665000 | 87787.91 | 13.2%

## CO1
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 15430 |  | CO # | 1 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 660 |  | -660 |  |  | 8.8
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 660 | 0 | -660 |  |  | 8.8 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
|  | Acoustical Ceilings | 9250
|  | Taping | 1721 |  | -1721
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 10971 | 0 | -1721
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference | Percent
| Overall Job Totals |  | 11631 | 15430 | 3799 | 24.62%

## CO2
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 161
| Change Amount: | 930 |  | CO # | 2 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 0 | 930 | 930 | 100%

## CO3
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 360 |  | CO # | 3 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 313 |  | -313 |  |  | 4.1733
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 313 | 0 | -313 |  |  | 4.1733 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 313 | 360 | 47 | 13.06%

## Updated Budget
Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Updated Contract : | 183740 |  | CO # | 3 |  |  | 2025-06-04
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 2000 |  | -2000 |  |  | 26.6667 | 91
|  | Clean-up | 2500 |  | -2500 |  |  | 33.3333 | 125
|  | Delivery | 1000 |  | -1000 |  |  | 13.3333 | 13
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0 | 16
|  | Layout | 1170 |  | -1170 |  |  | 15.6
|  | Rough Carpentry | 3451 |  | -3451 |  |  | 46.0133 | 48
|  | Finish Carpentry | 12388 |  | -12388 |  |  | 165.1733 | 309
|  | Doors | 4200 |  | -4200 |  |  | 56 | 34.5
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 7493 |  | -7493 |  |  | 99.9067 | 38
|  | Insulation | 974 |  | -974 |  |  | 12.9867 | 104
|  | Drywall | 18210 |  | -18210 |  |  | 242.8
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 3110 |  | -3110 |  |  | 41.4667
|  | Untion Dues | 0 | 9320.83 | 9320.83 |  |  | 0
|  | Overtime | 0 | 28605.71 | 28605.71 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0 | 4
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 56496 | 37926.54 | -18569.46 | 67.13% |  | 753.28 | 782.5 | -29.22
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 21290 |  | -21290
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  | 12623.32 | 12623.32
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 21290 | 12623.32 | -8666.68 | 59.29%
3 | Subcontractors
|  | Acoustical Ceilings | 63219
|  | Taping | 14501 | 70696.1 | 56195.1
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 77720 | 70696.1 | 56195.1 | 90.96%
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Contract Amount | Estimated Profit | Percent | Total Actual
| Overall Job Totals |  | 155506 | 183740 | 28234 | 15.37% | 121245.96 | 77.97%