## Original
Job Cost Budget
| Project Name: | PHSD 2026 |  | Job # | 209
| Contract Amount: | 360220 |  | Thru CO # | 0 |  |  | Last Update | 2026-02-24
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 3300 |  | -3300 |  |  | 44
|  | Clean-up | 3000 |  | -3000 |  |  | 40
|  | Delivery | 1000 |  | -1000 |  |  | 13.3333
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 1200 |  | -1200 |  |  | 16
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 19250 |  | -19250 |  |  | 256.6667
|  | Insulation | 2185 |  | -2185 |  |  | 29.1333
|  | Drywall | 31516 |  | -31516 |  |  | 420.2133
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Tectum | 3600 |  | -3600 |  |  | 48
|  | Caulking | 785 |  | -785 |  |  | 10.4667
|  | Overtime Hrs | 8220 |  | -8220 |  |  | 109.6
|  | Patching | 7320 |  | -7320 |  |  | 97.6
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 81376 | 0 | -81376 |  |  | 1085.0133 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 47057 |  | -47057
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 47057 | 0 | -47057
3 | Subcontractors
|  | K Buildings | 24379 |  | -24379
|  | Taping C4 | 55645 |  | -55645
0
|  | Subcontractor Totals | 80024 | 0 | -55645
4 | Other
|  | Equipment Rental |  |  | 0
|  | Bonding | 9000 |  | -9000
|  | Allowance | 53400 |  | -53400
|  | Contingency | 40000 |  | -40000
0
|  | Other Sub Totals | 102400 |  | -102400
|  |  | Budget | Contract Amount | Estimated Profit | Percent
| Overall Job Totals |  | 310857 | 360220 | 49363 | 13.7%

## SOV
Brighten SOV |  | Brighten SOV
PHSD 2026 |  | PHSD 2026
Pre-Con | 15300 | Pre-Con | 15300
Congress MS Phase 1 | 116270 | Congress MS Phase 1
|  | Framing Labor | 15700
|  | Framing Material | 4855
|  | Drywall Labor | 40670
|  | Drywall Material | 12000
|  | Tectum Labor | 6000
|  | Tectum Material | 14000
|  | Taping/Finishing Sub | 21045
|  | Equipment | 2000
Congress MS Phase 2 | 113300 | Congress MS Phase 2
|  | Framing Labor | 21500
|  | Framing Material | 5800
|  | Drywall Labor | 47000
|  | Drywall Material | 14000
|  | Taping/Finishing Sub | 24000
Congress Spray Applied Insualtion Subcontractor | 26000 | Congress Spray Applied Insualtion Subcontractor | 26000
|  | Equipment | 1000
Hawthorn ES | 5030 | Hawthorn ES
|  | Framing/Drywall Labor | 1200
|  | Framing/Drywall Material | 830
|  | Taping/Finishing Sub | 3000
Gerner EEC | 15620 | Gerner EEC
|  | Framing/Drywall Labor | 5620
|  | Framing/Drywall Material | 3000
|  | Taping/Finishing Sub | 7000
Lump Sum Allowance | 40000 | Lump Sum Allowance | 40000
Allowance Insualtion | 8000 | Allowance Insualtion | 8000
Allowance Patches | 8000 | Allowance Patches | 8000
Alt 1 Congress HVAC | 4200 | Alt 1 Congress HVAC | 4200
Alt 2 Congress SPED & RR | 8500 | Alt 2 Congress SPED & RR | 8500
Contract Amount | 360220 |  | 360220

## CO1
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 15430 |  | CO # | 1 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 660 |  | -660 |  |  | 8.8
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 660 | 0 | -660 |  |  | 8.8 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
|  | Acoustical Ceilings | 9250
|  | Taping | 1721 |  | -1721
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 10971 | 0 | -1721
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Difference | Percent
| Overall Job Totals |  | 11631 | 15430 | 3799 | 24.62%

## CO2
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 161
| Change Amount: | 930 |  | CO # | 2 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 0 |  | 0 |  |  | 0
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 0 | 0 | 0 |  |  | 0 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 0 | 930 | 930 | 100%

## CO3
CO Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Change Amount: | 360 |  | CO # | 3 |  |  | Last Update
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 0 |  | 0 |  |  | 0
|  | Clean-up | 0 |  | 0 |  |  | 0
|  | Delivery | 0 |  | 0 |  |  | 0
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0
|  | Layout | 0 |  | 0 |  |  | 0
|  | Rough Carpentry | 0 |  | 0 |  |  | 0
|  | Finish Carpentry | 313 |  | -313 |  |  | 4.1733
|  | Doors | 0 |  | 0 |  |  | 0
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 0 |  | 0 |  |  | 0
|  | Insulation | 0 |  | 0 |  |  | 0
|  | Drywall | 0 |  | 0 |  |  | 0
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 0 |  | 0 |  |  | 0
|  | Other | 0 |  | 0 |  |  | 0
|  | Overtime | 0 |  | 0 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 313 | 0 | -313 |  |  | 4.1733 | 0
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall |  |  | 0
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  |  | 0
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 0 | 0 | 0
3 | Subcontractors
Acoustical Ceilings
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 0 | 0 | 0
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Actual | Estimated Profit | Percent
| Overall Job Totals |  | 313 | 360 | 47 | 13.06%

## Updated Budget
Budget Update
| Project Name: | TUKHS GME Clinic @ Olathe Med |  | Job # | 162
| Updated Contract : | 183740 |  | CO # | 3 |  |  | 2025-06-04
| Section | Cost Code | $ Budgeted | $ Actual | Overrun | % | Change | Hrs Budgeted | Hrs Actual | Hrs Remaining
1 | Labor
|  | Supervision | 2000 |  | -2000 |  |  | 26.6667 | 91
|  | Clean-up | 2500 |  | -2500 |  |  | 33.3333 | 125
|  | Delivery | 1000 |  | -1000 |  |  | 13.3333 | 13
|  | Temp Protections | 0 |  | 0 |  |  | 0
|  | Demo | 0 |  | 0 |  |  | 0 | 16
|  | Layout | 1170 |  | -1170 |  |  | 15.6
|  | Rough Carpentry | 3451 |  | -3451 |  |  | 46.0133 | 48
|  | Finish Carpentry | 12388 |  | -12388 |  |  | 165.1733 | 309
|  | Doors | 4200 |  | -4200 |  |  | 56 | 34.5
|  | Exterior Framing | 0 |  | 0 |  |  | 0
|  | Sheathing | 0 |  | 0 |  |  | 0
|  | Interior Framing | 7493 |  | -7493 |  |  | 99.9067 | 38
|  | Insulation | 974 |  | -974 |  |  | 12.9867 | 104
|  | Drywall | 18210 |  | -18210 |  |  | 242.8
|  | Taping | 0 |  | 0 |  |  | 0
|  | Ceiling Grid | 0 |  | 0 |  |  | 0
|  | Ceiling Tile | 0 |  | 0 |  |  | 0
|  | Specialties | 3110 |  | -3110 |  |  | 41.4667
|  | Untion Dues | 0 | 9320.83 | 9320.83 |  |  | 0
|  | Overtime | 0 | 28605.71 | 28605.71 |  |  | 0
|  | Allowance Hrs | 0 |  | 0
|  | WO# | 0 |  | 0 |  |  | 0 | 4
|  | WO# | 0 |  | 0 |  |  | 0
|  | Labor Sub Totals | 56496 | 37926.54 | -18569.46 | 67.13% |  | 753.28 | 782.5 | -29.22
2 | Material
Supervision
|  | Temp Protections |  |  | 0
|  | Rough Carp |  |  | 0
|  | Finish Carp |  |  | 0
|  | Doors |  |  | 0
|  | Drywall | 21290 |  | -21290
|  | Ceiling |  |  | 0
|  | Specialties |  |  | 0
|  | Other |  | 12623.32 | 12623.32
|  | WO # |  |  | 0
|  | WO # |  |  | 0
|  | Material Sub Totals | 21290 | 12623.32 | -8666.68 | 59.29%
3 | Subcontractors
|  | Acoustical Ceilings | 63219
|  | Taping | 14501 | 70696.1 | 56195.1
|  | Other |  |  | 0
|  | Other |  |  | 0
|  | Subcontractor Totals | 77720 | 70696.1 | 56195.1 | 90.96%
4 | Other
|  | Equipment Rental |  |  | 0
|  | Engineering |  |  | 0
|  | Mileage |  |  | 0
|  | Tool Rental |  |  | 0
|  | Bonding |  |  | 0
|  | Allowance |  |  | 0
|  | Contingency |  |  | 0
|  | Dumpster |  |  | 0
|  | Other Sub Totals | 0 | 0 | 0
|  |  | Budget | Contract Amount | Estimated Profit | Percent | Total Actual
| Overall Job Totals |  | 155506 | 183740 | 28234 | 15.37% | 121245.96 | 77.97%